## Slide 1: An N+ (XBLA) Postmortem
http://www.thewayoftheninja.org
Mare Sheppard – Metanet Software Inc.
mareATmetanetsoftware.com
Nick Waanders – Slick Entertainment Inc.
nickATslickentertainment.com
Notes: <number>

## Slide 2: Getting Started
A well-developed prototype is worth its weight in gold. Actually, they tend not to weigh much, so really it’s worth the weight of something heavy.
Funding: self-funding by getting a loan or grant is the best way to go. You’ll get the best royalty deal, take the fewest financial risks and retain IP, copyright and your soul.

## Slide 3: Budget Breakdown

## Slide 4: Production, Development and Marketing
Development, testing and localizing teams need to be introduced so they can work closely with one another.
Even though Metanet’s role in the development part of N+ was more on the managerial side, we tried to be a useful and organized part of the process and to help everyone else out wherever and whenever possible. Go team!
Apparently, marketing your title makes a huge difference in terms of sales, so market constantly and creatively!

## Slide 5: There’s no ‘i’ in Teamocil...
Know your developer: when you’re outsourcing, consider a collaborative partnership rather than a work-for-hire contract or simple license deal.
Sharing royalties means both parties are equally invested in a successful final product, which is obviously a very good thing!

## Slide 6: Hang in There!

## Slide 7: N+ Development Diary
From Flash to XBLA
Notes: <number>

## Slide 8: February
Getting the company started.
Built a the game and level editor in C#.
Built a character editor tool.
Started C++ work on Eets codebase.
Recommendation:
Build a prototype in an ‘easy’ language.
Notes: <number>

## Slide 9: March
Ported C# game code to C++.
Multiplayer basics.
Built a UI system + tool + localization tool.
Recommendation:
Tackle the biggest problems first.
Notes: <number>

## Slide 10: April
Music + UI design contracted out.
Basic UI Flow
Multiplayer high-level layer.
Visual Effects Editor.
Recommendation:
Outsource early. People hate getting stuff at the last minute.
Notes: <number>

## Slide 11: May
Matchmaking, Leaderboards, Achievements.
All gameplay modes working.
Level editor.
Built debug tool.
Recommendation:
Build all tools in C#. It’s fast and very robust.
Notes: <number>

## Slide 12: June
Voice communication.
Integrating new UI design.
General gameplay code.
Lots of documentation.
Recommendation:
Don’t forget the time needed for documentation.
Notes: <number>

## Slide 13: July
Build Machine
All levels and features in the game.
Trial mode.
Ratings submission
Recommendation:
Get a build machine.
Notes: <number>

## Slide 14: August
VMC starts testing.
Main problem areas:
  Dialogs
  Network bandwidth
Showing the game at PAX
Recommendation:
Get your dialogs under control.
Notes: <number>

## Slide 15: September
Bug fixing:
  Multiplayer (lots of different modes)
  Disconnecting, Signing out
Localization of all Loc-Strings.
Recommendation:
Render your fonts to bitmaps if you’re supporting Asian languages.
Notes: <number>

## Slide 16: October
Bug fixing:
  TCR issues
  Terminology problems in localized content.
  Level names
Getting game ready for Certification
Recommendation:
Get a comfy chair in the office.
Notes: <number>

## Slide 17: November
Entered Certification process.
Oh no! More bugfixing!
Recommendation:
Don’t plan a vacation right after cert.
Notes: <number>

## Slide 18: December
Bug fixing
Daily calls about bug count.
Re-entered Certification process.
Recommendation:
More features means more bugs. Try to get less of both.
Notes: <number>

## Slide 19: January
Party!
Recommendation:
Party hard. You deserve it.
Notes: <number>

## Slide 20: What went right?
Design was set.
Homebuilt tools helped us a lot.
Top-secret focus testing at PAX.
We hit every milestone exactly on the day (except Cert)
Notes: <number>

## Slide 21: What could we improve?
Don’t fail Cert the first time.
Too many features and options.
Extra programmer at bugfixing stage.
Notes: <number>

## Slide 22: Questions?
Ask now or just send me an email:
nickATslickentertainment.com
Notes: <number>